## Summary
PROJECT STATUS REPORT
Monitoring PM Excel
Period: April – Mei 2026 · Generated: 14 Aug 2026 06:18
Project Code | P001 | Owner | Hanif Mu'taz
Category | Trial | Sponsor | Management
Start Date | 01 Apr 2026 | Target Date | 06 Mei 2026
Status | Execution | Priority | High
KEY METRICS
Overall Progress | Health | Open Issues | High/Critical Risks
72% | At Risk | 2 | 1
Overdue Tasks | Milestones Done
0 | 1
Health: At Risk — 1 high-impact issue · schedule variance 18% (waktu 90% vs progress 72%)

## Milestones
MILESTONES
Monitoring PM Excel · April – Mei 2026
Milestone | Owner | Target Date | Progress | Status
M1 - Planning | Hanif | 15 Apr 2026 | 100% | Done
M2 - Development | Hanif | 25 Apr 2026 | 80% | In Progress
M3 - Testing & Sign-off | Hanif | 06 Mei 2026 | 30% | In Progress

## Deliverables
DELIVERABLES
Monitoring PM Excel · April – Mei 2026
Deliverable | Milestone | Owner | Target Date | Progress | Status
Requirement & Template Excel | M1 - Planning | Hanif | 15 Apr 2026 | 100% | Done
VBA Report Engine | M2 - Development | Hanif | 25 Apr 2026 | 75% | In Progress
Validated PM Monitoring V1 | M3 - Testing & Sign-off | Hanif | 06 Mei 2026 | 30% | In Progress

## Tasks
TASKS
Monitoring PM Excel · April – Mei 2026
Task Code | Task | PIC | Status | Progress | Health | Due Date | Constraint | Next Action
P001.1 | Analisa kebutuhan data PM | Hanif | Done | 100% | On Track | 10 Apr
P001.2 | Desain template Excel | Hanif | Done | 100% | On Track | 15 Apr
P001.3 | Develop VBA import & parsing | Hanif | Done | 100% | On Track | 20 Apr
P001.4 | Develop VBA laporan per-short | Hanif | Done | 100% | On Track | 25 Apr
P001.5 | Develop VBA laporan monthly & weekly | Hanif | In Progress | 50% | Watch | 06 Mei |  | Lanjut coding aggregate
P001.6 | Meeting request feature baru | Hanif | In Progress | 40% | At Risk | 06 Mei |  | Siapkan deck request
P001.7 | Trial & validasi data real | Hanif | In Progress | 30% | At Risk | 06 Mei | Data belum matching manual | Cek hasil vs data manual
P001.8 | Review & sign-off ke direktur | Hanif | In Progress | 20% | At Risk | 06 Mei |  | Presentasi hasil trial

## Issues & Risks
ISSUES & RISKS
Monitoring PM Excel · April – Mei 2026
Type | Title | Severity | Impact | Probability | Owner | Status | Target Date | Next Action
Issue | Data real belum matching hasil manual | High | Validasi tertunda, sign-off berisiko mundur |  | Hanif | Open | 04 Mei | Cek formula parsing vs manual
Issue | Deck request feature belum siap | Medium | Meeting bisa mundur |  | Hanif | Open | 05 Mei | Selesaikan deck
Risk | Sign-off direktur mundur | High | Timeline mundur | High | Hanif | Mitigating | 06 Mei | Buffer 3 hari

## Progress History
PROGRESS HISTORY
Monitoring PM Excel · April – Mei 2026
Date | Entity | Previous | New | Delta | Updated By | Comment
01 Mei 09:00 | P001.7 | 0% | 10% | 10% | Hanif | Mulai trial
02 Mei 10:00 | P001.7 | 10% | 20% | 10% | Hanif | Setup data real
03 Mei 14:00 | P001.7 | 20% | 30% | 10% | Hanif | Cek batch pertama
20 Apr 11:00 | P001.5 | 0% | 25% | 25% | Hanif | Skeleton aggregate
28 Apr 16:00 | P001.5 | 25% | 50% | 25% | Hanif | Monthly report jalan

## Activity & Audit
ACTIVITY & AUDIT TRAIL
Monitoring PM Excel · April – Mei 2026
Date | User | Action | Entity | Field | Previous Value | New Value
03 Mei 14:00 | Hanif | status_change | P001.7 | progress | 20 | 30
01 Mei 08:30 | Hanif | created | Issue | - | - | Data belum matching
28 Apr 16:00 | Hanif | status_change | P001.5 | progress | 25 | 50
25 Apr 17:10 | Hanif | completed | P001.4 | status | in_progress | done